## Defects
Creation of Intelligent Bug Diagnosis Platform - Quality Assurance & Defect Tracker
Development Defect Log
Sl No | Submitted By | Submitted Date | Detected Sprint | Assigned To | Type Of Defect | Description | Action Taken | Action Taken Date | Status | Remarks
1 | QA Engineer | 2026-07-02 | Sprint 1 | Backend Dev | Data Cleaning | Raw HTML tags in crash log disrupting token chunking boundaries. | Added comprehensive regex tag stripping in preprocessor.py. | 2026-07-03 | Closed | Verified clean string normalization.
2 | AI Engineer | 2026-07-06 | Sprint 1 | AI Engineer | Preprocessing | Hexadecimal memory addresses causing vector embedding drift. | Added [HEX_ADDR] regex token masking before vectorization. | 2026-07-07 | Closed | Cosine similarity clustering improved by 14%.
3 | Backend Dev | 2026-07-08 | Sprint 1 | AI Engineer | Database / Perf | ChromaDB lookup exceeding 4000ms latency on cold start. | Reconfigured HNSW index parameters and tuned nearest neighbors to top-3. | 2026-07-09 | Closed | Retrieval latency dropped to ~140ms.
4 | QA Engineer | 2026-07-15 | Sprint 2 | AI Engineer | AI / Parsing | Log Analysis Agent misclassifying C++ SIGSEGV error lines. | Updated exception regex parser to detect POSIX signal headers. | 2026-07-16 | Closed | Accurately extracts failing C++ file and line number.
5 | QA Engineer | 2026-07-20 | Sprint 2 | AI Engineer | Classification | Triage Agent assigning 'Low' severity to NullPointer runtime crashes. | Added rule weighting to enforce 'Critical' severity on unhandled NPEs. | 2026-07-21 | Closed | Validated across 25 varied NPE crash scenarios.
6 | Frontend Dev | 2026-07-23 | Sprint 2 | Backend Dev | API / Validation | Backend API throwing HTTP 500 when only one-line summary is entered. | Made file upload optional and allowed single-line summary inputs. | 2026-07-24 | Closed | Graceful fallback handling works for all inputs.
7 | Frontend Dev | 2026-07-30 | Sprint 3 | Frontend Dev | Data Schema | UI rendering blank dark screen after analysis submission. | Aligned backend snake_case keys with frontend camelCase expectations. | 2026-07-31 | Closed | Resolved JSON rendering mismatch completely.
8 | AI Engineer | 2026-08-04 | Sprint 3 | AI Engineer | RAG Prompting | Root Cause Agent returning generic hypotheses for Java SQL timeouts. | Injected specific database connection pool context into the RAG prompt. | 2026-08-05 | Closed | Generates accurate connection leak hypotheses.
9 | QA Engineer | 2026-08-07 | Sprint 3 | Frontend Dev | UI / Styling | Remediation advice formatting overflowing code block containers. | Applied Tailwind CSS overflow-x-auto and sanitized text rendering. | 2026-08-10 | Closed | Clean layout preserved across screen sizes.
10 | QA Engineer | 2026-08-14 | Sprint 4 | Backend Dev | Active Learning | Newly confirmed fixes not appearing immediately in duplicate searches. | Implemented immediate in-memory index insertion upon confirmation. | 2026-08-17 | Closed | Live knowledge base growth verified.
11 | QA Engineer | 2026-08-18 | Sprint 4 | Full Stack Dev | Analytics Engine | Defect Pattern Analytics charts showing NaN for zero-count severities. | Added default zero-value dictionary initialization for all severity keys. | 2026-08-19 | Closed | Visual distributions render properly.
12 | Backend Dev | 2026-08-20 | Sprint 4 | Backend Dev | Concurrency | High CPU usage during batch test suite execution across 5 formats. | Configured bounded worker threads (torch.set_num_threads(2)). | 2026-08-21 | Closed | Smooth execution with <35% CPU utilization.

## Test_Cases
Creation of Intelligent Bug Diagnosis Platform - Unit & Functional Test Cases
Verification Test Suite Across Core Pipeline & Agent Modules
Test Case ID | Component / Module | Test Scenario Description | Defect Category | Input Data | Expected Result | Pass/Fail
UT_PRE_01 | Preprocessor | Verify HTML tag stripping from crash dumps | Data Cleaning | String: '<trace>Error at main</trace>' | Output contains clean string without '<trace>' tags | Pass
UT_PRE_02 | Preprocessor | Verify memory address masking to uniform token | Data Cleaning | String: 'Crash at 0x7FFF9B12C331' | Address converted to '[HEX_ADDR]' token | Pass
UT_CHK_01 | Text Chunker | Validate sliding window boundary overlap | Maintainability | 1,200 character multiline trace file | Chunks generated with exactly 50-token overlap | Pass
UT_VEC_01 | Vector Store | Check ChromaDB cosine distance retrieval latency | Performance | Query: 'CanvasRenderer texture size' | Retrieval completes in under 200ms with >= 90% score | Pass
UT_LOG_01 | Log Analysis Agent | Extract exception type from C++ SIGSEGV dump | AI / Parsing | File: 'test1_canvas_overflow.log' | Identifies 'std::runtime_error::NullPointer' | Pass
UT_LOG_02 | Log Analysis Agent | Isolate failing file path and line number | AI / Parsing | String: 'at CanvasRenderer.cpp:342' | Extracts 'CanvasRenderer.cpp' and line '342' | Pass
UT_TRG_01 | Triage Agent | Verify Critical severity classification for fatal crashes | Logical | String: 'Fatal connection leak detected' | Classifies Severity as 'Critical' and Priority 'P0' | Pass
UT_TRG_02 | Triage Agent | Check confidence score calculation format | Standards | Valid multi-agent analysis state | Confidence score formatted as integer percentage (85-100%) | Pass
UT_RCA_01 | Root Cause Agent | Validate RAG evidence synthesis against Mozilla dataset | AI Logic | File: 'graphics_nullpointer.log' | Hypothesis identifies GPU texture limit overflow (>16384px) | Pass
UT_DUP_01 | Duplicate Agent | Check semantic ranking of past resolved issues | AI Logic | Telemetry: 'HikariPool-1 timeout waiting' | Returns top-3 duplicates with similarity percentages | Pass
UT_REM_01 | Remediation Agent | Generate actionable fix advice and guidelines | AI Logic | Input: 'SQLTimeoutException' context | Outputs JDBC timeout adjustments & 3 best practice rules | Pass
UT_GRO_01 | KB Growth Loop | Verify dynamic addition of confirmed fix to vector DB | Functional | POST /api/v1/feedback/confirm-fix | Knowledge base size increases by +1 and records new ID | Pass
UT_ANA_01 | Analytics Engine | Verify defect pattern aggregation metrics | Functional | GET /api/v1/analytics | Returns JSON containing severity and component distributions | Pass
UT_UI_01 | Dashboard UI | Ensure responsive multi-agent findings display | UI / UX | Analysis payload with 5 agent outputs | All 5 cards render without layout overflow or text clipping | Pass