## Product Backlog
Creation of Intelligent Bug Diagnosis Platform with Fix Recommendation Assistance Group 2
Product Backlog (8-Week Agile Lifecycle: 2026-06-30 to 2026-08-24
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status | Story Points
Sprint 1 | Sprint 1 | US_01 | As a developer, I want to submit raw telemetry and crash logs (.log, .txt) so that unstructured text is cleaned and hex addresses are masked. | Must Have | None | Backend Dev | Done | 5
Sprint 1 | Sprint 1 | US_02 | As an AI engineer, I want recursive text chunking with 50-token overlap to preserve stack trace boundaries for vector search. | Must Have | US_01 | AI Engineer | Done | 5
Sprint 1 | Sprint 1 | US_03 | As a developer, I want ChromaDB vector store initialization seeded with historical defect benchmarks (Mozilla, Apache, Eclipse). | Must Have | US_02 | AI Engineer | Done | 8
Sprint 2 | Sprint 2 | US_04 | As a QA engineer, I want the Log Analysis Agent to extract exception types, failure points, and affected code paths into structured JSON. | Must Have | US_01 | Backend Dev | Done | 5
Sprint 2 | Sprint 2 | US_05 | As a triage lead, I want the Triage Agent to assign severity levels (Critical/High/Med/Low), priority tiers (P0–P3), and confidence scores. | Must Have | US_04 | AI Engineer | Done | 5
Sprint 2 | Sprint 2 | US_06 | As a developer, I want sequential multi-agent state orchestration so Log Analysis context is passed directly to downstream agents. | Must Have | US_04, US_05 | Backend Dev | Done | 5
Sprint 3 | Sprint 3 | US_07 | As an engineer, I want the Root Cause Agent to synthesize RAG evidence from ChromaDB to output evidence-backed cause hypotheses. | Must Have | US_03, US_06 | AI Engineer | Done | 8
Sprint 3 | Sprint 3 | US_08 | As an engineer, I want the Duplicate Detection Agent to surface top-3 matching historical defects with similarity percentages and fix commits. | Should Have | US_03 | AI Engineer | Done | 5
Sprint 3 | Sprint 3 | US_09 | As a developer, I want the Remediation Agent to output actionable code patches and engineering best practices based on root cause findings. | Must Have | US_07 | AI Engineer | Done | 5
Sprint 3 | Sprint 3 | US_10 | As a user, I want a unified Structured Findings Dashboard displaying all agent cards side-by-side in real-time. | Must Have | US_06, US_09 | Frontend Dev | Done | 8
Sprint 4 | Sprint 4 | US_11 | As a team lead, I want a Defect Pattern Analytics Dashboard tracking recurring failure themes, component frequencies, and severity distributions. | Must Have | US_10 | Frontend Dev | Done | 8
Sprint 4 | Sprint 4 | US_12 | As an engineer, I want a Knowledge Base Growth loop where confirmed fixes are dynamically indexed back into ChromaDB to improve future queries. | Must Have | US_08, US_09 | Backend Dev | Done | 8
Sprint 4 | Sprint 4 | US_13 | As a QA engineer, I want end-to-end multi-stack validation across C++, Java, Python, JavaScript, and Go crash scenarios. | Should Have | US_10, US_12 | QA Engineer | Done | 5

## Sprint Backlog
Creation of Intelligent Bug Diagnosis Platform - Sprint Task Backlogs
Tasks & Effort Tracking Across 4 Sprints (40 Working Days ¦ Excludes Weekends)
Sprint | US ID | Task ID | Task Description | Start Date | End Date | Assignee | Activity | Status | Effort (Hrs)
Sprint 1 | US_01 | TSK_01 | Design intake module & regex telemetry preprocessor | 2026-06-30 | 2026-07-02 | Backend Dev | Development | Completed | 12
Sprint 1 | US_01 | TSK_02 | Implement memory hex masking regex rule patterns | 2026-07-02 | 2026-07-06 | Backend Dev | Development | Completed | 8
Sprint 1 | US_02 | TSK_03 | Build recursive text sliding-window chunker with 50-token overlap | 2026-07-06 | 2026-07-08 | AI Engineer | Development | Completed | 12
Sprint 1 | US_03 | TSK_04 | Seed ChromaDB vector database with Mozilla/Apache/Eclipse defect datasets | 2026-07-08 | 2026-07-10 | AI Engineer | Infrastructure | Completed | 16
Sprint 1 | US_03 | TSK_05 | Perform Milestone 1 baseline retrieval validation sweeps | 2026-07-10 | 2026-07-13 | QA Engineer | Testing | Completed | 6
Sprint 2 | US_04 | TSK_06 | Construct Log Analysis Agent parser for stack traces and code paths | 2026-07-14 | 2026-07-16 | Backend Dev | Development | Completed | 14
Sprint 2 | US_05 | TSK_07 | Build Triage & Severity classification agent rule engine | 2026-07-16 | 2026-07-20 | AI Engineer | Development | Completed | 14
Sprint 2 | US_06 | TSK_08 | Implement stateful multi-agent sequential orchestrator | 2026-07-20 | 2026-07-23 | Backend Dev | Integration | Completed | 16
Sprint 2 | US_06 | TSK_09 | Design 2-agent findings UI panel with Tailwind dark layout | 2026-07-22 | 2026-07-24 | Frontend Dev | Development | Completed | 12
Sprint 2 | US_06 | TSK_10 | Execute multi-format agent accuracy benchmark tests | 2026-07-24 | 2026-07-27 | QA Engineer | Testing | Completed | 8
Sprint 3 | US_07 | TSK_11 | Implement RAG Root Cause Agent using vector context retrieval | 2026-07-28 | 2026-07-30 | AI Engineer | Development | Completed | 16
Sprint 3 | US_08 | TSK_12 | Develop Duplicate Detection Agent with cosine similarity ranking | 2026-07-30 | 2026-08-03 | AI Engineer | Development | Completed | 12
Sprint 3 | US_09 | TSK_13 | Build Remediation Agent for actionable patches & guidelines | 2026-08-03 | 2026-08-05 | AI Engineer | Development | Completed | 14
Sprint 3 | US_10 | TSK_14 | Implement Structured Findings Display with 5-agent container grid | 2026-08-05 | 2026-08-07 | Frontend Dev | Development | Completed | 16
Sprint 3 | US_10 | TSK_15 | Conduct Milestone 3 end-to-end multi-agent verification tests | 2026-08-07 | 2026-08-10 | QA Engineer | Testing | Completed | 8
Sprint 4 | US_11 | TSK_16 | Develop Defect Pattern Analytics aggregation engine & endpoints | 2026-08-11 | 2026-08-14 | Backend Dev | Development | Completed | 16
Sprint 4 | US_11 | TSK_17 | Build Analytics Dashboard UI (severity distribution, component charts) | 2026-08-13 | 2026-08-18 | Frontend Dev | Development | Completed | 14
Sprint 4 | US_12 | TSK_18 | Implement Knowledge Base Growth active learning loop endpoint | 2026-08-17 | 2026-08-19 | Backend Dev | Development | Completed | 12
Sprint 4 | US_13 | TSK_19 | Execute 5-stack test verification (C++, Java, Python, JS, Go) | 2026-08-19 | 2026-08-21 | QA Engineer | Testing | Completed | 10
Sprint 4 | US_13 | TSK_20 | Compile final documentation, user guide, and demo deliverables | 2026-08-21 | 2026-08-24 | Full Stack Dev | Documentation | Completed | 8

## Stand up Meeting
Creation of Intelligent Bug Diagnosis Platform - Daily Standup Log
Standup Notes & Impediment Tracking (Mon-Fri Weekdays Only)
Sprint | Working Day | Date | Identified Impediment | Action Taken & Resolution
Sprint 1 | Day 3 | 2026-07-02 | Raw multiline stack trace uploads throwing HTTP 413 error in backend middleware. | Expanded body-parser capacity in FastAPI server to accept raw telemetry strings up to 50MB.
Sprint 1 | Day 8 | 2026-07-09 | Hexadecimal addresses creating noise during semantic embedding vectorization. | Implemented regex token replacement to mask memory addresses with uniform [HEX_ADDR] tokens.
Sprint 2 | Day 12 | 2026-07-15 | Repetitive embedding calculations causing latency during high-frequency log analysis. | Integrated @functools.lru_cache on the embedding pipeline to cache vector representations.
Sprint 2 | Day 17 | 2026-07-22 | Log Analysis Agent regex parser failing on nested Java $$Lambda$ stack frames. | Refactored capture patterns to support multi-line fallback and recursive stack frame parsing.
Sprint 3 | Day 22 | 2026-07-29 | Duplicate tracking detector encountering race conditions during concurrent execution. | Isolated asynchronous request state contexts and applied thread isolation wrappers.
Sprint 3 | Day 27 | 2026-08-05 | UI rendering blank screen due to casing mismatch between backend JSON and React keys. | Standardized response payload structure to match frontend expectations across all agent outputs.
Sprint 4 | Day 32 | 2026-08-12 | Root Cause Agent returning generic reasoning when historical similarity scores fell below 80%. | Configured ChromaDB distance indexing to Cosine similarity and added domain-specific fallback logic.
Sprint 4 | Day 38 | 2026-08-20 | Batch test execution of 5 defect logs causing transient CPU core spikes. | Configured torch.set_num_threads(2) bounds to maintain smooth execution with <35% CPU utilization.

## Retrospection
Creation of Intelligent Bug Diagnosis Platform - Sprint Retrospectives
Continuous Improvement Across All 4 Sprints (Dates Strictly Mon-Fri)
Sprint | Start Date | End Date | Role | Start Doing | Stop Doing | Continue Doing | Action Taken
Sprint 1 | 2026-06-30 | 2026-07-13 | Backend Dev | Strict payload validation | Hardcoding sample traces | Modular preprocessors | Added regex sanitizers & schema validation
Sprint 1 | 2026-06-30 | 2026-07-13 | AI Engineer | HNSW vector indexing | Full table scans | ChromaDB seeded storage | Configured top-3 nearest neighbor retrieval
Sprint 2 | 2026-07-14 | 2026-07-27 | AI Engineer | Few-shot agent prompts | Manual trace inspection | Stateful orchestration | Standardized severity classification logic
Sprint 2 | 2026-07-14 | 2026-07-27 | Frontend Dev | Reusable agent cards | Hardcoded CSS stylesheets | Tailwind dark theme UI | Refactored React component architecture
Sprint 3 | 2026-07-28 | 2026-08-10 | AI Engineer | RAG evidence groundings | Unverified hypotheses | Cosine similarity scoring | Injected historical defect resolution context
Sprint 3 | 2026-07-28 | 2026-08-10 | QA Engineer | Automated multi-stack tests | Manual copy-paste sweeps | Regression suites | Created automated test harness for all agents
Sprint 4 | 2026-08-11 | 2026-08-24 | Full Stack Dev | Dynamic KB indexing | Static dataset reliance | Analytics aggregation | Implemented active learning growth endpoint
Sprint 4 | 2026-08-11 | 2026-08-24 | Team Lead | Comprehensive user guides | Ad-hoc documentation | Structured code reviews | Compiled complete project report & API guide